## Sheet2
PROJECT PLAN TEMPLATE
PROJECT TITLE
Northwest Gaming Application
WBS NO. | TASK NAME | STATUS | DURATION in hours
1 | Sprint 0 |  | 180
1.1 | – User stories prioritization | Done | 20
1.2 | – ER-Diagram development | Done | 25
1.3 | – Sample data | Done | 20
1.4 | – Schedule management plan | In-progress | 25
1.5 | – Cost estimation | Done | 20
1.6 | – Proposed UI screens development | In-progress | 30
1.7 | – Jira setups | Done | 20
1.8 | – User authorization | Done | 20
2 | Sprint 1 |  | 180
2.1 | Planning the User stories | To-Do | 50
2.1.1 | As a User I want to login/Signup for the game. | To-Do
2.1.2 | As a user I want to create a team. | To-Do
2.1.3 | As a User I want to Join a Team. | To-Do
2.1.4 | As a User(captain) I want to accept/decline an invite of a player. | To-Do
2.1.5 | As a user I want to act as the huntmaster and create quest. | To-Do
2.1.6 | As a User(huntmaster) I want to add multiple locations in a single quest. | To-Do
2.1.7 | As a User I want to join a competition. | To-Do
2.2 | – Sprint 1 Implementation of all the user stories planned | To-Do | 100
2.3 | – Sprint 1 Demo and client Acceptance | To-Do | 30
2.5 | – MVP 1 release | To-Do
3 | Sprint 2 |  | 200
3.1 | – Sprint 2 Planning Of User stories | To-Do | 50
3.1.1 | As a User I want to join a competition when it starts. | To-Do
3.1.2 | As a User I want to know about the scoring details of the competition. | To-Do
3.1.3 | As a User I want to look at the points scored by the team. | To-Do
3.1.4 | As a user I want to know how the team points are calculated. | To-Do
3.1.5 | As User I want to know the limit of the players per team. | To-Do
3.1.6 | As a user I want to leave the team and join other team. | To-Do
3.1.7 | As a User I want to change my nick name. | To-Do
3.1.8 | As a User I want to create multiple accounts under one user id. | To-Do
3.1.9 | As a user I want to know how many more locations are left to be found out. | To-Do
3.1.10 | As a user I want hints if I am unable to crack the clue. | To-Do
3.4 | – Sprint 2 Implementation of all the User stories | To-Do | 120
3.3 | – Sprint 2 Demo | To-Do | 30
3.5 | – MVP 2 release | To-Do
4 | Sprint 3 | To-Do | 180
4.1 | – Sprint 3 Planning of user stories | To-Do | 50
4.1.1 | As a user I want to know if there are any points reduced if I use the hints field. | To-Do
4.1.2 | As a User I want assistance in finding a location. | To-Do
4.1.3 | As a user I want to hear instructions while going to that location. | To-Do
4.1.4 | As a user I wish to mute the instructions. | To-Do
4.1.5 | As a user I wish to mute the instructions. | To-Do
4.1.6 | As a user I want to look at all the settings available for the game. | To-Do
4.1.7 | As a User I want to know if I can create a quest for the competition. | To-Do
4.2 | – Sprint 3 Implementation of all the User stories | To-Do | 100
4.3 | – Sprint 3 Demo and Client Acceptance | To-Do | 30
4.5 | – MVP 3 release | To-Do
5 | Sprint 4 (GDP-2) all sprints |  | 540
5.1 | – Sprint 4 Planning of User stories | To-Do
5.2 | – Iteration of all the tasks | To-Do
5.3 | – Testing the application and client approval | To-Do
5.5 | – MVP 4 release | To-Do