## Sheet2
PROJECT PLAN TEMPLATE
PROJECT TITLE
Northwest Gaming Application
WBS NO. | TASK NAME | STATUS | DURATION in hours
1 | Sprint 0 |  | 200
1.1 | – User stories prioritization | Done | 25
1.2 | – ER-Diagram development | Done | 25
1.3 | – Sample data | Done | 25
1.4 | – Schedule management plan | In-progress | 25
1.5 | – cost estimation | Done | 20
1.6 | – proposed UI screens development | In-progress | 30
1.7 | – Jira setups | Done | 24
1.8 | – User authorization | Done | 26
2 | Sprint 1 |  | 200
2.1 | – Sprint 1 planning | To-Do | 35
2.2 | – Sprint 1 execution | To-Do | 35
2.3 | – Sprint 1 Demo and user authorization | To-Do | 35
2.4 | – Sprint 1 implementation | To-Do | 45
2.5 | – MVP 1 release | To-Do | 50
3 | Sprint 2 |  | 200
3.1 | – Sprint 2 planning | To-Do | 35
3.2 | – Sprint 2 execution | To-Do | 35
3.3 | – Sprint 2 Demo and user authorization | To-Do | 35
3.4 | – Sprint 2 implementation | To-Do | 45
3.5 | – MVP 2 release | To-Do | 50
4 | Sprint 3 |  | 200
4.1 | – Sprint 3 planning | To-Do | 35
4.2 | – Sprint 3 execution | To-Do | 35
4.3 | – Sprint 3 Demo and user authorization | To-Do | 35
4.4 | – Sprint 3 implementation | To-Do | 45
4.5 | – MVP 3 release | To-Do | 50
5 | Sprint 4 (GDP-2) all sprints |  | 600
5.1 | – Sprint 4 planning | To-Do | 100
5.2 | – Sprint 4 execution | To-Do | 140
5.3 | – Sprint 4 Demo and user authorization | To-Do | 140
5.4 | – Sprint 4 implementation | To-Do | 115
5.5 | – MVP 4 release | To-Do | 105