## Sheet1
PROJECT COST ESTIMATE
PROJECT TITLE
Northwest Gaming Application
WBS NO. | TASK NAME | STATUS | DURATION in hours | TOTAL TEAM COST | TOTAL COST PER WEEK
1 | Sprint 0 |  | 200
1.1 | User stories prioritization | Done | 25 | 350 | 8750
1.2 | ER-Diagram development | Done | 25 | 350 | 8750
1.3 | Sample data | Done | 25 | 350 | 8750
1.4 | Schedule management plan | In-progress | 25 | 350 | 8750
1.5 | cost estimation | Done | 20 | 350 | 7000
1.6 | proposed UI screens development | In-progress | 30 | 350 | 10500
1.7 | Jira setups | Done | 24 | 350 | 8400
1.8 | User authorization | Done | 26 | 350 | 9100
2 | Sprint 1 |  | 200
2.1 | Sprint 1 planning | To-Do | 35 | 350 | 12250
2.2 | Sprint 1 execution | To-Do | 35 | 350 | 12250
2.3 | Sprint 1 Demo and user authorization | To-Do | 35 | 350 | 12250
2.4 | Sprint 1 implementation | To-Do | 45 | 350 | 15750
2.5 | MVP 1 release | To-Do | 50 | 350 | 17500
3 | Sprint 2 |  | 200
3.1 | Sprint 2 planning | To-Do | 35 | 350 | 12250
3.2 | Sprint 2 execution | To-Do | 35 | 350 | 12250
3.3 | Sprint 2 Demo and user authorization | To-Do | 35 | 350 | 12250
3.4 | Sprint 2 implementation | To-Do | 45 | 350 | 15750
3.5 | MVP 2 release | To-Do | 50 | 350 | 17500
4 | Sprint 3 |  | 200
4.1 | Sprint 3 planning | To-Do | 35 | 350 | 12250
4.2 | Sprint 3 execution | To-Do | 35 | 350 | 12250
4.3 | Sprint 3 Demo and user authorization | To-Do | 35 | 350 | 12250
4.4 | Sprint 3 implementation | To-Do | 45 | 350 | 15750
4.5 | MVP 3 release | To-Do | 50 | 350 | 17500
4 | Sprint 4 (GDP-2) |  | 200
4.1 | Sprint 4 planning | To-Do | 35 | 350 | 12250
4.2 | Sprint 4 execution | To-Do | 35 | 350 | 12250
4.3 | Sprint 4 Demo and user authorization | To-Do | 35 | 350 | 12250
4.4 | Sprint 4 implementation | To-Do | 45 | 350 | 15750
4.5 | MVP 4 release | To-Do | 50 | 350 | 17500
| TOTAL PROJECT COST |  |  |  | 350000